## Project Manager Report
New | Plant | Project Manager | BkUp Proj Mgr | OrderDate | Serial Number | Customer | Project | SalesRep | First Online Date | Due in next 2 weeks | Due in next 4 weeks | Past Due | Status
| Phoenix | Candy Juhnke |  | 2025-09-25 | PMI-6781 | SPECIALIZED TESTING & CONSTRUCTION | I-3 - Florence AZ Medical Intake/X-Ray Ctr 2-Story | George Avila | 2026-08-25 |  |  |  | ACTIVE
| Southeast | Candy Juhnke | Crystal Myers | 2025-11-19 | SMM-21145 | MODULAR MANAGEMENT GROUP | ACIC GERMANY- II-B | Jason King |  |  |  |  | ACTIVE
| Southeast | Crystal Myers |  | 2024-07-16 | SMM-21003 | MOBILE MODULAR- AUBURNDALE | 96X60 DISNEY CONFERENCE BUILDING 160MPH | Shawn Durante | 2025-02-04 |  |  |  | ACTIVE
| Southeast | Crystal Myers | Candy Juhnke | 2025-02-24 | SMM-21055 | KITCHENS TO GO | 12'X56' VA-PREP MODULE (FL,TX,SC) | Jason King | 2025-07-12 |  |  |  | ACTIVE
| Southeast | Crystal Myers | Candy Juhnke | 2025-02-24 | SMM-21056 | KITCHENS TO GO | 12'X56' VA-WASH MODULE (FL,TX,SC) | Jason King | 2025-07-19 |  |  |  | ACTIVE
| Southeast | Crystal Myers | Candy Juhnke | 2025-02-24 | SMM-21057 | KITCHENS TO GO | 12'X56' VA-COOK MODULE (FL,TX,SC) | Jason King | 2025-07-26 |  |  |  | ACTIVE
| SSI | Crystal Myers | Candy Juhnke | 2025-12-11 | 7669 | MOBILEASE MODULAR SPACE, INC. | 140'X68' MIKE DOVER A-B 8-CR 120MPH 57#SN/LD | Josh Ellis | 2026-02-04 |  |  |  | ACTIVE
| SSI | Crystal Myers | Candy Juhnke | 2025-12-11 | 7670 | MOBILEASE MODULAR SPACE, INC. | CUSTOM COMPLEX MIKE DOVER 8-CR C-D 120MPH 57#SN/LD | Josh Ellis | 2025-12-29 |  |  |  | ACTIVE
| SSI | Crystal Myers | Candy Juhnke | 2025-12-11 | 7671 | MOBILEASE MODULAR SPACE, INC. | 84'X55' MIKE DOVER MULTI PURPOSE 120MPH 57#SN/LD | Josh Ellis | 2026-01-21 |  |  |  | ACTIVE
| SSI | Crystal Myers | Candy Juhnke | 2025-12-11 | 7672 | MOBILEASE MODULAR SPACE, INC. | 14'X55' MIKE FOOD SERVICE 120MPH 57#SN/LD | Josh Ellis | 2026-01-26 |  |  |  | ACTIVE
| Southeast | Crystal Myers | Candy Juhnke | 2025-02-24 | SMM-21054 | KITCHENS TO GO | 12'X56' VA-WASH MODULE (GOOGLE SUMMERVILLE) | Jason King | 2025-05-22
| Southeast | Crystal Myers | Crystal Myers | 2025-06-24 | SMM-21103 | AFFORDABLE STRUCTURES - TAVARES | 2B 24x50 SCIF WA State PE Certification 160mph | Roger Diamond | 2026-02-19 |  |  |  | ACTIVE
| Southeast | Crystal Myers | Matthew McDaniel | 2024-09-30 | SMM-21020 | MODULAR MANAGEMENT GROUP | Patrick Space Force Base Building 1, 160MPH | Don Eisman | 2025-04-07
| Indicom | Hector Vazquez | Michael Caracciolo | 2025-07-15 | 25B579-584 | MODULAR MANAGEMENT GROUP | POINT MAGU NAVAL BASE (REACT) CA | Jason King | 2026-02-26 |  |  | CustSgnOff | ACTIVE
| NWBS | Matthew McDaniel |  | 2025-07-21 | 25250 | Mobile Modular Management Corporation | 168x66 Hanford AMPS Project MMG | Mitch Quintana | 2026-01-27 |  |  |  | ACTIVE
| Phoenix | Matthew McDaniel | Candy Juhnke | 2025-11-04 | PMI-6798 | MOBILE MODULAR MANAGEMENT | M/B - 52x68 & 36x72 Aambe Health Facility | George Avila | 2026-01-30 |  |  |  | ACTIVE
| SSI | Matthew McDaniel | Michael Caracciolo | 2025-10-20 | 7547 | MODULAR GENIUS, INC. | BASF Georgia 2 Story 120 MPH | Barbara Hicks | 2025-11-20 |  |  |  | ACTIVE
| Phoenix | Michael Caracciolo |  | 2025-10-02 | DO-0521-1-25 | WILLIAMS SCOTSMAN | B- LASD Div 4 Facility | Casey Knipp | 2026-08-24 |  |  |  | DRAWINGS ONLY
| Promod | Michael Caracciolo | Candy Juhnke | 2025-09-15 | SME-23038 | CASSONE LEASING, INC. | DSNY - Brooklyn Lot Cleaning Garage Facility | Dean Long | 2026-02-16 |  |  | CustSgnOff LongLd | ACTIVE
| Phoenix | Michael Caracciolo | Candy Juhnke | 2025-07-28 | PMI-6749-6763 | MOBILE MODULAR MANAGEMENT CORP. | R-OCC Homeless Units - CD 15 E 116th Place | Casey Knipp | 2026-09-18 |  |  |  | HOLD